## Scope Definition
FCC Implementation Scope | In Scope? | Details |  |  | Feature Clean | In Scope Flag
[10 empty] | Yes_List | No_List
Dimensions | [8 empty] | YES | 1 | 0
Account | YES | 2000 | 4 |  | Account | 1 |  |  | NO | 2
Account Alternate Hierarchies | YES | 2 |  |  | Account Alternate Hierarchies | 1 |  |  |  | 3
Rationalization of CoA | YES | 3 |  |  | Rationalization of CoA | 1
Multi-Currency | YES | 5 | 1 |  | Multi-Currency | 1 |  |  |  | 4
Reporting Currency | YES | 2 | 2 |  | Reporting Currency | 1
Entity | YES | 25 | 4 |  | Entity | 1
Entity Redesign | NO |  |  |  | Entity Redesign | 0
Entity Alternate Hierarchies | YES | 2 |  |  | Entity Alternate Hierarchies | 1 | Select the necessary roles for this engagement
Scenario | YES | 2 | 3 |  | Scenario | 1 | PM USA | TRUE
Multi-GAAP | YES |  | 1 |  | Multi-GAAP | 1 | PM India | TRUE
Custom Dimensions | YES | 2 | 2 |  | Custom Dimensions | 1 | Architect USA | TRUE
Alternate Hierarchies in Custom Dimensions | YES | 2 |  |  | Alternate Hierarchies in Custom Dimensions | 1 | Delivery Lead India | TRUE
Additional Alias Tables | YES | 1 | 1 |  | Additional Alias Tables | 1 | Sr. Delivery Lead India | TRUE
[6 empty] | 0 | App Lead USA | TRUE
Application Features |  |  |  |  | Application Features | 0 | App Lead India | TRUE
Elimination | YES |  | 1 |  | Elimination | 1 | App Developer USA | FALSE
Custom Elimination Requirement | NO |  |  |  | Custom Elimination Requirement | 0 | App Developer India | TRUE
Consolidation Journals | YES |  | 4 |  | Consolidation Journals | 1 | Integration Lead USA | TRUE
Journal Templates | YES | 1 |  |  | Journal Templates | 1 | Integration Developer India | TRUE
Parent Currency Journals | YES |  |  |  | Parent Currency Journals | 1 | Reporting Lead India | FALSE
Ownership Management | NO |  | 0 |  | Ownership Management | 0 | Security Lead India | FALSE
Enhanced Organization by Period | NO |  |  |  | Enhanced Organization by Period | 0
Equity Pickup | NO |  |  |  | Equity Pickup | 0
Partner Elimination | NO |  |  |  | Partner Elimination | 0
Configurable Consolidation Rules | NO |  |  |  | Configurable Consolidation Rules | 0
Cash Flow | YES |  | 2 |  | Cash Flow | 1
Supplemental Data Collection | NO |  | 0 |  | Supplemental Data Collection | 0
Enterprise Journals | NO |  | 0 |  | Enterprise Journals | 0
Approval Process | YES |  | 2 |  | Approval Process | 1
Historic Overrides | YES |  | 4 |  | Historic Overrides | 1
Task Manager | NO |  | 0 |  | Task Manager | 0
Audit | YES |  | 1 |  | Audit | 1
0
Application Customization |  |  |  |  | Application Customization | 0
Data Forms | YES | 5 | 11 |  | Data Forms | 1
Dashboards | NO | 3 | 0 |  | Dashboards | 0
0
Calculations |  |  |  |  | Calculations | 0
Business Rules | YES | 3 | 7 |  | Business Rules | 1
Member Formula | YES | 20 | 11 |  | Member Formula | 1
Ratios | YES |  | 2 |  | Ratios | 1
Custom KPIs | NO |  | 0 |  | Custom KPIs | 0
0
Security |  |  |  | 6 | Security | 0
Secured Dimensions | YES | 1 | 2 |  | Secured Dimensions | 1
Number of Users | YES | 20 | 4 |  | Number of Users | 1
0
Historical Data |  |  |  | 12 | Historical Data | 0
Historical Data Validation | YES | 2 | 4 |  | Historical Data Validation | 1
Data Validation for Account Alt Hierarchies | YES |  | 4 |  | Data Validation for Account Alt Hierarchies | 1
Data Validation for Entity Alt Hierarchies | YES |  | 4 |  | Data Validation for Entity Alt Hierarchies | 1
Historical Journal Conversion | YES |  | 2 |  | Historical Journal Conversion | 1
0
Integrations |  |  |  | 8 | Integrations | 0
Files Based Loads | NO | 2 | 0 |  | Files Based Loads | 0
Direct Connect Integrations | YES | 1 | 4 |  | Direct Connect Integrations | 1
Outbound Integrations | NO |  | 0 |  | Outbound Integrations | 0
Pipeline | NO | 1 | 0 |  | Pipeline | 0
Custom Scripting | YES | 2 | 4 |  | Custom Scripting | 1
0
Reporting |  |  |  |  | Reporting | 0
Management Reports | YES | 5 | 4 |  | Management Reports | 1
Consolidation Reports | NO |  | 0 |  | Consolidation Reports | 0
Consolidation Journal Reports | YES | 1 | 2 |  | Consolidation Journal Reports | 1
Intercompany Reports | YES | 1 | 4 |  | Intercompany Reports | 1
Task Manager Reports | NO |  | 0 |  | Task Manager Reports | 0
Enterprise Journal Reports | NO |  | 0 |  | Enterprise Journal Reports | 0
Smart View Reports | YES | 3 | 2 |  | Smart View Reports | 1
0
Automations |  |  |  | 4 | Automations | 0
Automated Data loads | YES |  | 2 |  | Automated Data loads | 1
Automated Consolidations | YES |  | 2 |  | Automated Consolidations | 1
Backup and Archival | NO |  | 0 |  | Backup and Archival | 0
Metadata Import | NO |  | 0 |  | Metadata Import | 0
Testing/Training |  |  |  |  | Testing/Training | 0
Unit Testing | YES |  | 1 |  | Unit Testing | 1
UAT | YES |  | 2 |  | UAT | 1
SIT | YES |  | 2 |  | SIT | 1
Parallel Testing | YES | 3 | 6 |  | Parallel Testing | 1
User Training | YES |  | 4 |  | User Training | 1
Transition |  |  |  |  | Transition | 0
Go Live | YES |  | 1 |  | Go Live | 1
Hypercare | YES |  | 1 |  | Hypercare | 1
Documentations |  |  |  |  | Documentations | 0
RTM | YES |  | 1 |  | RTM | 1
Design Document | YES |  | 1 |  | Design Document | 1
System Configuration Document | YES |  | 1 |  | System Configuration Document | 1
Change Management |  |  |  |  | Change Management | 0
Admin Desktop Procedures | YES |  | 1 |  | Admin Desktop Procedures | 1
End User Desktop Procedures | YES |  | 1 |  | End User Desktop Procedures | 1
Project Management |  |  |  |  | Project Management | 0
Project Management | YES |  | 1 |  | Project Management | 1
130
Implementation Tiering Process
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Approximate Number of Accounts
Note on D7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of alternate hierarchies in Account dimension
Note on D9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Currencies
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Reporting Currencies
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Entities
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of alternate hierarchies in Entity dimension
Note on D14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Scenarios
Note on D16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Custom dimensions
Note on D17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of alternate hierarchies in Custom dimensions
Note on D24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of journal templates
Note on D40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Data Forms
Note on D41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of dashboards
Note on D44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Insertion Rules
Note on D45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Member Formula
Note on D46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of translation overrides
Note on D50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of secured dimensions
Note on D51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of users
Note on D54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of years in historical data validation
Note on D60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number if file based loads
Note on D61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Direct Integrations
Note on D63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Pipelines
Note on D64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number Custom Scripting
Note on D67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Management Reports
Note on D68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Consolidation Reports
Note on D69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Consolidation Journal Reports
Note on D70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Intercompany Reports
Note on D71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Task Manager Reports
Note on D72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Enterprise Journal Reports
Note on D73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Smart View Reports
Note on D85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Parallel testing

## Scope of Service
Tier 3 - Enhanced Scope
Scope of Services
Under this SOW, Donyati will work with Client to provide Services noted below. Actual activities, work items, schedule and deliverables would be jointly managed by Donyati and Client based on the Client’s business priorities.
The scope of this engagement is focused on the implementation of the following application modules:
Oracle EPM Enterprise – Financial Consolidation and Close
Donyati Services consist of the following:
Implementation of Financial Consolidation and Close
Dimensions
Account dimension (~ 2000accounts) will be configured based on the current Chart of Accounts. CoA Rationalization will be performed. Standard Trial Balance will be incorporated into the Account dimension to support the following financial statements.
Up to 2 Account alternate hierarchies will be developed
Entity - (~25) will be configures based on the currenct structure. In addtion, up to 2 alternate hierarchies will be developed
Currency dimension will be configures with 5 Currencies.There will be 2 Reporting Currency
Movement dimension will be configured to support Cash Flow and Roll-forward activities.
Year, Period, View, Consolidation, Intercompany, and Data Source dimensions will be configured to support consolidation and reporting
Custom dimensions will be leveraged to support additional reporting requirements. Specific use of 2 Custom Dimensions will be determined during requirements and design
Custom dimensions will have 2 alternate hierarchies
Application Features
Standard elimination capabilities will be provided
Consolidation Journal will be enabled and 1 Journal Template will be created
Ownership Management is not in scope, No Equity pickup
Our of box Configuration of indirect Cash Flow will be used.
Approval Process will be used in the application.
Task Manager will be used in the application to support Financial Consolidation and Close.
Application Customization
Custom Data Forms – If required, up to 5 Custom Data Forms will be developed to support Financial Consolidation and Close.
Calculations
Custom Business Rules – If required, up to 3 Custom Business rules will be developed to support Financial Consolidation and Close.
Member Formulas – If required, up to 20 Member Formulas will be developed to support Financial Consolidation and Close.
Translation override will be set up if required

## Timings
Timings
The engagement start date is 13-Aug-2025
The engagement end date is 30-Apr-2026
Go-live support will be provided and additional capabilities will be added per a subsequent Statement of Work expected to be started immediately following the completion of this Statement of Work.
This SOW assumes 8 months to complete Financial Consolidation and Close.
Completion of Services and Deliverables agreed upon is subject to, among other things, appropriate cooperation, obtaining the necessary information, and timely response to inquiries. The chart below shows the estimated hours per month for each resource role. At the conclusion of Requirements and Design, Donyati will revise the implementation timeline to incorporate agreed upon requirements and design elements. Donyati and Client will review and approve the revised implementation timeline before moving into the Development Phase.
Resource Role/Monthly Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
PM USA | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118
PM India | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118
Architect USA | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58
Sr. Delivery Lead India | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118
Delivery Lead India | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118
App Lead USA | 234 | 234 | 234 | 234 | 234 | 234 | 234 | 234
App Lead India | 234 | 234 | 234 | 234 | 234 | 234 | 234 | 234
App Developer India | 223 | 223 | 223 | 223 | 223 | 223 | 223 | 223
Integration Lead USA | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55
Integration Developer India | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55

## KDD Items
KDD Items
KDD01 - General Application Configuration
KDD02 - Metadata Configuration
KDD03 - FCC Consolidations and Other Calculations
KDD04 - Reports and Data Form Configuration
KDD05 - Cash Flow
KDD06 - Journal Process
KDD07 - Integrations
KDD08 - Historical Data Source and Validations
KDD09 - Automations
KDD10 - Approval Process
KDD11 - Application Security
KDD12 - Audit

## App Tiers Definition
% of FTE Efforts
| Weightage |  |  |  | USA | India | USA | India | India | USA | India | USA | India | USA | India | India | India
| Range |  |  | Hours | PM | PM | Architect | Sr. Delivery Lead | Delivery Lead | App Lead | App Lead | App Developer | App Developer | Integration Lead | Integration Developer | Reporting Lead | Security Lead
Tier 1 - Jumpstart | 0 | 60 | Project Initiation and Planning | 18 | 50% | 50% | 100% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | TECO | 52
Tier 2 - Foundation Plus | 61 | 100 | Creating and Managing EPM Cloud Infrastructure | 6 | 50% | 50% | 0% | 50% | 50% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | Summit Polymers
Tier 3 - Enhanced Scope | 101 | 150 | Requirement Gathering, Read back and Client Sign-off | 44 | 50% | 50% | 100% | 50% | 50% | 100% | 100% | 0% | 0% | 20% | 20% | 0% | 0% | Labrie
Tier 4 - Advanced Enablement | 151 | 200 | Design | 42 | 50% | 50% | 100% | 50% | 50% | 100% | 100% | 0% | 0% | 20% | 20% | 0% | 0% | Jtekt | 100
Tier 5 - Full Spectrum | 201 | 999 | Build and Configure FCC | 148 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | Delta
|  |  | Setup Application Features | 96.5 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | Cooper Std | 133
|  |  | Application Customization | 72 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | Central Ins
|  |  | Calculations | 126 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | MTW
|  |  | Security | 24 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 20% | 20% | 0% | 100%
|  |  | Historical Data | 552 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0%
|  |  | Integrations | 140 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0%
|  |  | Reporting | 140 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 0%
|  |  | Automations | 64 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0%
|  |  | Testing/Training | 244 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 50% | 50% | 20% | 0%
|  |  | Transition | 96 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 0%
|  |  | Documentations | 36 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 0%
|  |  | Change Management | 44 | 50% | 50% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 0%
|  |  |  | 1892.5 | 946.25 | 946.25 | 460.5 | 946.25 | 946.25 | 1874.5 | 1874.5 | 1782.5 | 1782.5 | 436 | 436 | 188.8 | 24

## Effort Estimation
FCC Tasks | Time in hours | In Scope? | Details | Total Time | Final Estimate | in Days
Project Initiation and Planning | 12 |  |  | 18 | 18 | 2.25
Kickoff Meetings | 1 | YES
Project Governance | 1 | YES
Communication Plan | 1 | YES
Resource Allocation | 2 | YES
RAID Log | 1 | YES
Project Plan | 4 | YES
Plan Status Meetings and SteerCo Meeting Schedule | 2 | YES
Creating and Managing EPM Cloud Infrastructure | 6 |  |  | 6 | 6 | 0.75
Creating and Setting up Oracle EPM Cloud instances | 2 | YES
Prelim FCC User Provisioning | 4 | YES | 20 | 0
Requirement Gathering, Read back and Client Sign-off | 32 |  |  | 44 | 44 | 5.5
Requirement Gathering Sessions | 8 | YES
Current CoA details | 4 | YES
CoA Hierarchies | 4 | YES
Current Consolidation Model | 4 | YES
Sample Reports | 2 | YES
Dimension Details | 4 | YES
Develop Requirement Treaceability Matrix | 4 | YES
Formal RTM Signoff | 2 | YES
Design | 26 |  |  | 42 | 42 | 5.25
Design Document | 8 | YES
Key Design Decision Document | 8 | YES
Internal Peer Review | 4 | YES
Design and KDD Reviews | 4 | YES
Design Approval from Client | 2 | YES
Build and Configure FCC | 88 |  |  | 104 | 148 | 18.5
Application Configuration | 2 | YES
Account | 16 | YES
Account Alternate Hierarchies | 8 | YES | 2 | 16
Rationalization of CoA | 24 | YES
Multi Currency | 1 | NO | 0 | 0
Reporting Currency | 0.5 | YES | 2 | 1
Data Source | 0.5 | YES
Entity | 8 | YES
Entity Redesign | 8 | NO
Entity Alternate Hierarchies | 4 | YES | 2 | 8
Movement | 4 | YES
Scenario | 1 | YES | 2 | 2
Multi-GAAP | 2 | YES
Custom Dimensions | 4 | YES | 2 | 8
Alternate Hierarchies in Custom Dimensions | 4 | YES | 2 | 8
Additional Alias Tables | 1 | YES | 1 | 1
Setup Application Features | 79.5 |  |  | 95.5 | 96.5 | 12.0625
Elimination | 0.5 | YES
Consolidation Journals | 1 | YES
Journal Templates | 1 | YES | 1 | 1
Ownership Management | 4 | NO
Enhanced Organization by Period | 4 | NO
Equity Pickup | 8 | NO
Partner Elimination | 8 | NO
Configurable Consolidation Rules | 8 | NO | 0 | 0
Cash Flow | 8 | YES
Supplemental Data Collection | 8 | NO
Enterprise Journals | 8 | NO
Approval Process | 8 | YES
Historic Overrides | 4 | YES
Task Manager | 8 | NO
Audit | 1 | YES
Application Customization | 8 |  |  | 20 | 72 | 9 | Total n reports, 1/2 of the reports - Low Complexity
Data Forms | 4 | YES | 5 | 52 |  |  | 1/4 of the reports - Medium complexity
Dashboards | 4 | NO | 0 | 0 |  |  | 1/4 of the reports - High complexity
Calculations | 15 |  |  | 27 | 126 | 15.75 | Total n member formula, 1/2 of the member formula - Low Complexity
Business Rules | 8 | YES | 3 | 44 |  |  | 1/4 of the member formula - Medium complexity
Member Formula | 1 | YES | 20 | 55 |  |  | 1/4 of the member formula - High complexity
Ratios | 4 | YES
Custom KPIs | 2 | NO | 0 | 0
Security | 4 |  |  | 16 | 24 | 3
Secured Dimensions | 2 | YES | 1 | 4
Number of Users | 2 | YES | 20 | 4
Historical Data | 60 |  |  | 72 | 552 | 69
Historical Data Validation | Calc | YES | 2 | 360 |  |  | 15 days for the first 4 months, and 10 days for each subsequent year
Data Validation for Account Alt Hierarchies | 20 | YES | 2 | 40
Data Validation for Entity Alt Hierarchies | 20 | YES | 2 | 40
Historical Journal Conversion | 20 | YES | 2 | 40
Integrations | 80 |  |  | 92 | 140 | 17.5
Files Based Loads | 16 | NO | 0 | 0
Direct Connect Integrations | 16 | YES | 1 | 16
Outbound Integrations | 16 | NO | 0 | 0
Pipeline | 16 | NO | 0 | 0
Custom Scripting | 16 | YES | 2 | 32
Reporting | 40 |  |  | 52 | 140 | 17.5
Management Reports | 8 | YES | 5 | 52
Consolidation Reports | 4 | NO | 0 | 0
Consolidation Journal Reports | 4 | YES | 1 | 4
Intercompany Reports | 8 | YES | 1 | 8
Task Manager Reports | 4 | NO | 0 | 0
Enterprise Journal Reports | 4 | NO | 0 | 0
Smart View Reports | 8 | YES | 3 | 24
Automations | 52 |  |  | 64 | 64 | 8
Automated Data loads | 16 | YES
Automated Consolidations | 8 | YES
Backup and Archival | 12 | NO
Metadata Import | 16 | NO
Testing/Training | 152 |  |  | 164 | 244 | 30.5
Unit Testing | 40 | YES
UAT | 40 | YES
SIT | 16 | YES
Parallel Testing | 40 | YES | 2 | 80
User Training | 16 | YES
Transition | 80 |  |  | 96 | 96 | 12
Go Live | 40 | YES
Hypercare | 40 | YES
Documentations | 24 |  |  | 36 | 36 | 4.5
RTM | 8 | YES
Design Document | 8 | YES
System Configuration Document | 8 | YES
Change Management | 32 |  |  | 44 | 44 | 5.5
Admin Desktop Procedures | 16 | YES
End user Desktop Procedures | 16 | YES
|  |  |  | Hours | Days | Months
|  |  |  | 1892.5 | 236.5625 | 7.8854

## Sheet1 (hidden)
Resource Role / | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Monthly Hours
Project Manager - USA (50%) | 44 | 88 | 84 | 84 | 92 | 72 | 88 | 108
Project Manager - India (50%) | 44 | 88 | 84 | 84 | 92 | 72 | 88 | 108
Solution Architect - FCC -– USA | 88 | 88 | 34 | 34 | 37 | 29 | 35 | 112
Integration Architect -– USA | 44 | 88 | 34 | 34 | 5
Integration Lead -– India |  | 176 | 168 | 168 | 184 | 144 | 176 | 168 | 160
Application Lead - FCC -– USA |  | 176 | 168 | 168 | 184 | 144 | 176 | 168 | 160
Sr. Application Lead - FCC - India |  | 176 | 168 | 168 | 184 | 144 | 176 | 144
Application Lead - Reports - India |  | 176 | 168 | 168 | 184 | 144 | 176 | 144
Melissa - Change Management Supportgt | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 6
7010

## Definitions (hidden)
Scope of Services
Under this SOW, Donyati will work with Client to provide Services noted below. Actual activities, work items, schedule and deliverables would be jointly managed by Donyati and Client based on the Client’s business priorities.
The scope of this engagement is focused on the implementation of the following application modules:
Oracle EPM Enterprise – Financial Consolidation and Close
Donyati Services consist of the following:
Implementation of Financial Consolidation and Close
Dimensions
Account dimension (~ 2000accounts) will be configured based on the current Chart of Accounts. CoA Rationalization will be performed. Standard Trial Balance will be incorporated into the Account dimension to support the following financial statements.
Up to 2 Account alternate hierarchies will be developed
Entity - (~25) will be configures based on the currenct structure. In addtion, up to 2 alternate hierarchies will be developed
Currency dimension will be configures with 5 Currencies.There will be 2 Reporting Currency
Movement dimension will be configured to support Cash Flow and Roll-forward activities.
Year, Period, View, Consolidation, Intercompany, and Data Source dimensions will be configured to support consolidation and reporting
Custom dimensions will be leveraged to support additional reporting requirements. Specific use of 2 Custom Dimensions will be determined during requirements and design
Custom dimensions will have 2 alternate hierarchies
Application Features
Standard elimination capabilities will be provided
Consolidation Journal will be enabled and 1 Journal Template will be created
Ownership Management is not in scope, No Equity pickup
Our of box Configuration of indirect Cash Flow will be used.
Approval Process will be used in the application.
Task Manager will be used in the application to support Financial Consolidation and Close.
Application Customization
Custom Data Forms – If required, up to 5 Custom Data Forms will be developed to support Financial Consolidation and Close.
Calculations
Custom Business Rules – If required, up to 3 Custom Business rules will be developed to support Financial Consolidation and Close.
Member Formulas – If required, up to 20 Member Formulas will be developed to support Financial Consolidation and Close.
Translation override will be set up if required
Key Design Decisions
General Application Configuration |  | General Application Configuration
Metadata Configuration |  | Metadata Configuration
FCC Consolidations and Other Calculations |  | FCC Consolidations and Other Calculations
Reports and Data Form Configuration |  | Reports and Data Form Configuration
Ownership Management
Cash Flow |  | Cash Flow
Journal Process |  | Journal Process
Integrations |  | Integrations
Historical Data Source and Validations |  | Historical Data Source and Validations
Automations |  | Automations
Approval Process |  | Approval Process
Task Manager
Supplemental Data Collection
Enterprise Journals
Application Security |  | Application Security
Audit |  | Audit
Timings
The engagement start date is 18-Nov-2025
The engagement end date is 31-Jul-2026
Go-live support will be provided and additional capabilities will be added per a subsequent Statement of Work expected to be started immediately following the completion of this Statement of Work.
This SOW assumes 8 months to complete Financial Consolidation and Close.
Completion of Services and Deliverables agreed upon is subject to, among other things, appropriate cooperation, obtaining the necessary information, and timely response to inquiries. The chart below shows the estimated hours per month for each resource role. At the conclusion of Requirements and Design, Donyati will revise the implementation timeline to incorporate agreed upon requirements and design elements. Donyati and Client will review and approve the revised implementation timeline before moving into the Development Phase.
Resource Role/Monthly Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
PM USA | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118
PM India | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118
Architect USA | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58
Sr. Delivery Lead India | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118
Delivery Lead India | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118
App Lead USA | 234 | 234 | 234 | 234 | 234 | 234 | 234 | 234
App Lead India | 234 | 234 | 234 | 234 | 234 | 234 | 234 | 234
App Developer USA | 223 | 223 | 223 | 223 | 223 | 223 | 223 | 223
App Developer India | 223 | 223 | 223 | 223 | 223 | 223 | 223 | 223
Integration Lead USA | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55
Integration Developer India | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55
Reporting Lead India | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
Security Lead India | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3